#### Security:

- Is there a Confidentiality Clause? – Check the NDA box in Vision! Highlight for PM, Accounting, and Marketing

- Do they require background checks, drug tests, fingerprinting, badges onsite? – should be ONLY employees on site

- We have Background checks available from hiring – do they need more recent? Or from a specific company?

- Do they require specific companies for tests, fingerprinting, or badging?

- Note any specific requirements for Badges (pictures, company, etc.)

- Check for Conflict of Interest details that seem more extreme or specific – make a note if necessary

#### Client Info:

Corgan Associates, Inc.

111 Congress Ave Suite 850

Austin, TX 78701

#### Project Info/Scope:

#### Specialty Design and Consulting services for the Sinton ISD New HS Replacement and New Field House

#### Compensation:

$167,000.00

#### Invoicing:

#### Reimbursables:

Page 4- There are no reimbursables except for the final printing of 100% CD’s for bidding

SD 15%

DD 20%

CD 30%

BIDDING/PERMITTING 5%

CA 30%

#### Schedule:

Schematic Design Phase January 1 – March 31, 2021

Consultant Kick-off Meeting 02/12/2021

50% SD Design Package Deadline 02/24/2021

100% SD Design Package Deadline 03/30/2021

Design Development Phase April 1 – June 30, 2021

50% DD Design Package Deadline 04/29/2021

100% DD Design Package Deadline 05/27/2021

Construction Document Phase July 1 – September 30, 2021

50% CD Design Package Deadline 07/22/2021

100% CD QA/QC Package Deadline 09/06/2021

Bluebeam Mark-up Session Deadline 09/20/2021

100% CD Issued for Bidding Set Deadline 09/27/2021

Bidding/Procurement Phase October 4 – November 2, 2021

100% Issued for Construction Set Deadline 11/18/2021 (incorporates all addenda and cost saving items)

Construction Administration Phase January 1, 2022 – June 30, 2024

#### Governing Contract:

- Consultant or Prime (C401: can be found in 1.3)

#### Governing Law:

#### Professional Credit:

- Are we allowed to use photos/renderings for marketing?

- Do they require prior written authorization?

- Is there a confidentiality clause? (copy/paste at the top of the notes and check the NDA box in Vision)

#### Additional Services:

- Compare to Proposal

- Typically add services require prior written authorization – make note of this.

#### Insurance:

- Compare Limits to Master Certificate of Insurance (located G:\Admin Assistant\Insurance)

- Everything except for Professional Liability insurance can be supplemented with the Umbrella Insurance to reach limits.

- Umbrella Insurance is $5M

- Any limit requirements for Umbrella must be subtracted first.

- Extract Insurance pages and attach to Insurance Certificate request form

- Maintain Insurance for how many years?

#### Subconsultants:

- Make a note if anything concrete is said about Subs – none allowed, they are subject to terms, or if they are named.

#### Ownership:

- Who owns the Documents/Instruments of Service?

- Who can continue to use them?

- Check for a Liability Clause: will we be responsible for unauthorized use of our documents/instruments?

#### Indemnification:

- Look for:

- “Defend” – Julie usually wants to strike this word

- “Alleged/Threatened” – Julie wants to be made aware of these words in context

- “Any and All, entirely” – Julie usually wants to strike these

- Insert: Negligent (Act), Actual, Reasonable (Attorney’s Fees)

- Dual Indemnification? Consultant AND Prime?

#### Dispute Resolution:

- Disputes not involving Owner:

- Disputes involving Owner: (found in the Prime)

- Which methods of dispute resolution have client and/or owner chosen, and in what order?

- Binding or Non-binding

- Waiver of Jury

- Any unorthodox resolutions? (Sometimes, schools will use their own internal dispute resolutions first – read those)

#### Termination:

- Make sure Consultant will be paid for services performed if terminated without cause

- Make sure Consultant may terminate (same as Architect in Prime)

#### Records Retention:

- Does the contract specify how long records must be kept available?

- How long?

- What kind(s) of records?

- Any other requirements?